## Slide 1: SFA Workback (ADO Walkthrough)
 | Oct 1st - 12th | SPRINT 1 (OCT 15th – 19th) | SPRINT 2 (OCT 22nd – 26th) | SPRINT 3 (OCT 29TH– NOV 16TH ) | SPRINT 4 (NOV 19th – 30th ) | SPRINT 5 (Dec 3rd– 7th ) | SPRINT 6 (DEC 10th – 21st ) | GA 1st Jan 2019
 | PLANNING [1 WEEKS] Exam Objective Domain Creation, review and Feedback Feedback and Iterations addressing feedback | Exam Objective Domain Complete [1 WEEKS] Exam Objective Domain Finalized Course Content Outline and component planning started | Course Outline Finalized [1 WEEKS] Course scope / Modules/Lesson/Topic outlines Finalized Video Topic Identification About Page Creation a | DEVELOPMENT [3 WEEKS] Content Development Initial publish to studio platform | DEVELOPMENT [2 WEEKS] Video / Graphic Development Question Authoring | Staging and Initial Private Testing [1 WEEK] Course Staging and Validation in studio Studio Platform Configuration Hand off to pdets Private Testing by author and bug fixing | BETA RELEASE [2 WEEK] Testing and bug fixing Private Reviews and feedback implementation Final Bug fixing and final staging for release | General Availability
ACHIEVEMENTS | Exam OD draft creation External and Internal Reviews | Exam OD Finalized and Locked Final Exam OD handed off for Item dev Course Content Outline work started, initial drafts | Course scope locked and agreed. Content Outline defined and finalized Identification of Video Topics need, components to re-use, new video topics needing recording Creation of Course About page and hand off to pdets. | Content Development - creation of module/lesson/topic content. Core of Content complete and handed off to git repo and pdets Initial Publish to platform Bug fixing during auto publish stage | Video/Graphic recording and editing Graphic creation End of Module and Course question authoring Hand off of video content to pdets for CC and staging | Final Staging and configuration in studio Prep for hand off to pdets for Beta release | Pdets Test pass (both Functional and UAT ) Bug Fixing Continuing bug fixing, and any updates required post Beta Release Sign off from Dev Final Release prep to Production | Monitoring course performance / forums Engaging with students as they progress Implementation of any production fixes required
 | PLANNING |  |  | DEVELOPMENT |  | RELEASE |  | Post Release Bug Fixing
1st Jan 2019
GA
Drop 1
* Contingent on TSI dependencies and timelines
Drop 2
Drop 3
Beta Release

## Slide 2: XX-YYY: Azure Fundamentals Objective Domain
Understand Cloud Concepts
  Describe the benefits and considerations of using cloud services;
  Describe the differences between Infrastructure-as-a-Service (IaaS), Platform-as-a-Service (PaaS) and Software-as-a-Service (SaaS);
  Describe the differences between Public, Private and Hybrid cloud models;
Understand Core Azure Services
  Understand the core Azure architectural components
  Describe some of the core products available in Azure
  Describe some of the solutions available on Azure
  Understand Azure management tools
Understand Security, Privacy, Compliance and Trust
  Understand securing network connectivity in Azure
  Describe core Azure Identity services;
  Describe security tools and features of Azure
  Describe Azure governance methodologies
  Understand monitoring and reporting options in Azure
  Understand privacy, compliance and data protection standards in Azure
Understand Azure Pricing and Support
  Understand Azure subscriptions
  Understand planning and management of costs
  Understand the support options available with Azure
  Describe Azure Service Level Agreements (SLAs);
  Understand service lifecycle in Azure
Notes: Understand Cloud Concepts
  Describe the benefits and considerations of using cloud services;
    Understand terms such as High Availability, Scalability, Elasticity, Agility, Fault Tolerance,
and Disaster Recovery;
    Understand the principles of economies of Scale
    Understand the differences between Capital Expenditure (CapEx) and Operational Expenditure (OpEx)
    Understand the consumption-based model
  Describe the differences between Infrastructure-as-a-Service (IaaS), Platform-as-a-Service (PaaS) and Software-as-a-Service (SaaS);
    Describe Infrastructure-as-a-Service (IaaS),
    Describe Platform-as-a-Service (PaaS);
    Describe Software-as-a-Service (SaaS);
    Compare and contrast the three different service types;
  Describe the differences between Public, Private and Hybrid cloud models;
    Describe Public cloud;
    Describe Private cloud;
    Describe Hybrid cloud;
    Compare and contrast the three different cloud models;
Understand Core Azure Services
  Understand the core Azure architectural components
    Describe Regions;
    Describe Availability Zones;
    Describe Resource Groups;
    Describe Azure Resource Manager;
    Describe the benefits and usage of these core Azure architectural components;
  Describe some of the core products available in Azure
    Describe products available for Compute such as Virtual Machines, Virtual Machine Scale Sets, App Service and Functions;
    Describe products available for Networking such as Virtual Network, Load Balancer, VPN Gateway, Application Gateway and Content Delivery Network;
    Describe products available for Storage such as Blob Storage, Disk Storage, File Storage and Archive Storage;
    Describe products available for Databases such as CosmosDB, Azure SQL Database, Azure Database Migration service and Azure SQL Data Warehouse;
    Describe the Azure Marketplace and its usage scenarios;
  Describe some of the solutions available on Azure
    Describe Internet of Things (IoT) and some of the products that are available for IoT on Azure such as IoT Fundamentals, IoT Hub and IoT Central;
    Describe Big Data and Analytics and some of the products that are available for Big Data and Analytics such as SQL Data Warehouse, HDInsight and Data Lake Analytics;
    Describe Artificial Intelligence (AI) and some of the products that are available for AI such as Azure Machine Learning Service and Studio;
    Describe Serverless computing and some of the Azure products that are available for serverless computing such as Azure Functions, Logic Apps and App grid;
    Describe the benefits and outcomes available using these Azure solutions;
  Understand Azure management tools
    Understand Azure tools such as Azure CLI, PowerShell and the Azure Portal;
    Understand Azure Advisor;
Understand Security, Privacy, Compliance and Trust
  Understand securing network connectivity in Azure
    Describe Azure Firewall;
    Describe Azure DDoS Protection;
    Describe Network Security Group (NSG);
    Choose an appropriate Azure security solution
  Describe core Azure Identity services;
    Understand the difference between authentication and authorization;
    Describe Azure Active Directory;
    Describe Azure Multi-Factor Authentication;
  Describe security tools and features of Azure
    Describe Azure Security;
    Understand Azure Security center usage scenarios;
    Describe Key Vault;
    Describe Azure Information Protection (AIP);
    Describe Azure Advanced Threat Protection (ATP);
  Describe Azure governance methodologies
    Describe Azure Policies;
    Describe Initiatives;
    Describe Role-Based Access Control (RBAC);
    Describe Locks;
    Describe Azure Advisor security assistance;
  Understand monitoring and reporting options in Azure
    Describe Azure Monitor;
    Describe Azure Service Health;
    Understand the use cases and benefits of Azure Monitor and Azure Service Health;
  Understand privacy, compliance and data protection standards in Azure
    Understand Industry compliance terms such as GDPR, ISO and NIST;
    Understand the Microsoft Privacy Statement;
    Describe the Trust center;
    Describe the Service Trust Portal;
    Describe Compliance Manager;
    Understand how to determine if Azure is compliant for a particular business need;
    Understand Azure Government services;
    Understand Azure Germany services;
Understand Azure Pricing and Support
  Understand Azure subscriptions
    Describe what is an Azure Subscription
    Understand the uses and options with Azure subscriptions
  Understand planning and management of costs
    Understand options for purchasing Azure products and services;
    Understand options around Azure Free account;
    Understand the factors affecting costs such as resource types, services, locations, ingress and egress traffic;
    Understand Zones for billing purposes
    Understand the Pricing calculator
    Understand the Total Cost of Ownership (TCO) calculator
    Understand some best practices to minimum Azure costs such as performing cost analysis, creating spending limits and quotas, using tags to identify cost owners, using Azure reservations and using Azure Advisor recommendations;
    Describe Azure Cost Management;
  Understand the support options available with Azure
    Understand support plans that are available such as Dev, Standard, Professional Direct and Premier;
    Understand how to open a support ticket;
    Understand available support channels outside of support plan channels;
    Describe the Knowledge Center
  Describe Azure Service Level Agreements (SLAs);
    Describe a Service Level Agreement (SLA);
    Understand how to determine an SLA for a particular Azure product or service;
  Understand service lifecycle in Azure
    Understand Public and Private Preview features;
    Understand how to access Preview features;
    Understand the term General Availability (GA);
    Monitoring feature updates